## Slide 1
S | B RESOURCES
Governance
& Risk
Structure, clarity, and confidence.
Design decision rights, manage risk, and keep transformation on course.
Risk Assessment Template
Governance Structure One-Pager
Transformation Initiative Status Report
Standard Operating Procedure (SOP)
soufianeboudarraja.com | Dark Version

## Slide 2
RISK ASSESSMENT TEMPLATE
Layout A
Risk Register
Log, score, and own every risk — update at each governance checkpoint
S | B · Risk Assessment · soufianeboudarraja.com
Low 1–3
Medium 4–7
Med-High 8–14
High 15–25
#
Risk Description
Category
Likelihood
(1–5)
Impact
(1–5)
Score
Owner
Mitigation Action
Review
Date
1
Financial
4
5
20
CFO
2
Operational
3
4
12
Ops Lead
3
Compliance
5
4
20
Legal
4
Reputational
2
3
6
Comms
5
Technology
3
4
12
CTO
6
Operational
4
3
12
Ops Lead
7
Financial
2
3
6
Finance
8
Technology
3
4
12
IT Mgr
9
Compliance
4
3
12
Legal
10
Reputational
2
2
4
HR

## Slide 3
RISK ASSESSMENT TEMPLATE
Layout B
Risk Heat Map
Plot each risk by likelihood and impact — prioritise the top-right quadrant
S | B · Risk Assessment · soufianeboudarraja.com
IMPACT →
LIKELIHOOD →
1
5
2
4
3
3
4
2
5
1
5
10
15
20
25
4
8
12
16
20
3
6
9
12
15
2
4
6
8
10
1
2
3
4
5
1
2
3
4
5
6
Risk Reference
1
Data Privacy Breach
2
Budget Overrun
3
Change Resistance
4
Regulatory Fail
5
Scope Creep
6
Vendor Delay
CRITICAL
LOW

## Slide 4
RISK ASSESSMENT TEMPLATE
Layout C
Risk Summary — Card View
One card per priority risk — use for leadership briefings and steering reviews
S | B · Risk Assessment · soufianeboudarraja.com
20
R1
Data Privacy Breach
Compliance
Owner:
Legal
Mitigation:
2FA, data retention policy, GDPR audit Q3
12
R2
Budget Overrun
Financial
Owner:
CFO
Mitigation:
Monthly budget gate review + variance alert
15
R3
Change Resistance
Operational
Owner:
HR / CM
Mitigation:
Training programme + Q&A channels + sponsor comms
8
R4
Regulatory Non-Compliance
Compliance
Owner:
Legal
Mitigation:
Compliance checklist at design gate
6
R5
Scope Creep
Operational
Owner:
PMO
Mitigation:
Change control board + weekly scope check
3
R6
Vendor / System Delay
Technology
Owner:
IT Lead
Mitigation:
SLA clauses + parallel workstream contingency

## Slide 5
GOVERNANCE STRUCTURE
Layout A
Governance Structure — Three-Tier Model
Who decides, who executes, and who adapts — at each level of the organisation
S | B · Governance Structure · soufianeboudarraja.com
TIER 1
Steering Committee
Sets strategy, approves major budgets and scope, resolves cross-functional escalations
Can decide:
Approve / reject initiatives over €50K · Change strategic direction · Resolve governance disputes
Members:
CxO sponsors · Finance lead · Ops · IT · Risk / Legal
Cadence: Monthly + ad hoc escalations
↓ escalates to
TIER 2
Project & Programme Teams
Plans, executes, and tracks delivery. Manages day-to-day decisions within approved scope
Can decide:
Approve implementation details · Manage timelines and dependencies · Escalate risks to Tier 1
Members:
PMO lead · Process owners · SMEs · Data analysts · Change managers
Cadence: Weekly stand-up + bi-weekly steering update
↓ escalates to
TIER 3
Local / Operational Teams
Implements changes in the field. Adapts within defined limits. Raises local risks and blockers
Can decide:
Adapt processes within approved scope · Raise issues to Tier 2 · Validate change effectiveness
Members:
Front-line managers · Ops staff · Local IT · Quality reps
Cadence: Daily ops + weekly sync with Tier 2

## Slide 6
GOVERNANCE STRUCTURE
Layout B
Decision Rights Matrix
Which decisions each tier owns, approves, or is consulted on
S | B · Governance Structure · soufianeboudarraja.com
D
Decide
A
Approve
C
Consult
I
Inform
Decision
Steering
Committee
Project
Team
Local /
Ops Team
Initiative launch / kill
D
C
I
Budget approval (> €50K)
D
C
I
Budget approval (< €50K)
C
D
I
Scope change (major)
D
C
I
Scope change (minor)
I
D
C
Risk escalation response
D
C
I
Process design choices
C
D
I
Tool / vendor selection
A
D
C
SOP sign-off
A
D
C
Staff communications
C
D
I
Local process adaptation
I
C
D

## Slide 7
GOVERNANCE STRUCTURE
Layout C
Governance Cadence Planner
Set your rhythm — who meets when, what they decide, and what they report up
S | B · Governance Structure · soufianeboudarraja.com
Forum / Meeting
Tier
Attendees
Agenda
Output
DAILY
Ops Stand-up
T3
Local ops team
Blockers / output review
Action items
WEEKLY
Project Stand-up
T2
PMO + workstream leads
Progress / risks / decisions
Status update + decisions
Risk Review
T2
PMO + Risk
Top 5 risk status
Mitigation actions
BI-WEEKLY
Steering Update
T1
Committee + PMO
Portfolio health / escalations
Decisions + guidance
MONTHLY
Steering Committee
T1
All CxO + PMO lead
Strategy, budget, priorities
Approved changes / decisions
Budget Review
T1
Finance + CxO
Spend vs. plan + variances
Budget adjustments
QUARTERLY
Governance Review
T1
Full committee
Health check / lessons / roadmap
Updated governance charter

## Slide 8
TRANSFORMATION STATUS REPORT
Layout A
Initiative Status Report
Quarterly view: status, milestones, risks, budget variance, and next actions
S | B · Status Report · soufianeboudarraja.com
Initiative
Owner
RAG
Key Milestone
This Period
Top Risk /
Mitigation
Budget
Variance
Decision
Needed
O2C Process Redesign
J. Müller
G
Value-stream map signed off
IT dep. delay / parallel workstream
+2%
Approve scope ext.
ERP Data Migration
S. Li
A
Data cleansing 60% complete
Quality gaps / daily QA sprint
+9%
Release contingency
Automation Wave 1
A. Patel
G
Invoice bot live in UAT
Low adoption / change mgmt boost
-3%
Compliance Uplift
M. Garcia
R
GDPR audit overdue
Regulatory breach / legal mobilised
+18%
Escalate to Tier 1
Workforce Upskilling
T. Nguyen
G
30 staff trained (Wave 1)
Availability / stagger schedule
0%
Customer Portal MVP
L. Brown
A
UX design delayed 2 weeks
Vendor lag / interim resource
+6%
Approve resource

## Slide 9
TRANSFORMATION STATUS REPORT
Layout B
Initiative Dashboard — Card View
One card per initiative — use for exec briefings and steering reviews
S | B · Status Report · soufianeboudarraja.com
ON
TRACK
O2C Process Redesign
Owner: J. Müller
72% complete
Risk: IT dependency
Next: Pilot go-live: wk 8
AT
RISK
ERP Data Migration
Owner: S. Li
48% complete
Risk: Data quality
Next: QA sprint complete: wk 6
ON
TRACK
Automation Wave 1
Owner: A. Patel
85% complete
Risk: Adoption
Next: UAT sign-off: wk 5
OFF
TRACK
Compliance Uplift
Owner: M. Garcia
22% complete
Risk: GDPR audit
Next: Legal review: urgent
ON
TRACK
Workforce Upskilling
Owner: T. Nguyen
60% complete
Risk: Availability
Next: Wave 2 kick-off: wk 9
AT
RISK
Customer Portal MVP
Owner: L. Brown
38% complete
Risk: Vendor lag
Next: UX revision: wk 7

## Slide 10
TRANSFORMATION STATUS REPORT
Layout C
30-Day Action Plan
Decisions needed from leadership, blockers, and the next 30-day sprint
S | B · Status Report · soufianeboudarraja.com
Decisions Needed
Release contingency budget for ERP migration (Owner: CFO — by Fri)
Approve resource for Customer Portal MVP (Owner: CxO — by EOW)
Escalate Compliance Uplift to Tier 1 — GDPR audit at risk
Confirm Wave 2 training schedule with HR (Owner: T. Nguyen — wk 9)
Sign off O2C pilot scope extension (Owner: Steering Comm. — wk 8)
Active Blockers
ERP: data quality issues slowing migration — QA sprint needed
Compliance: GDPR audit not started — legal escalation raised
Portal: vendor 2 weeks behind — interim resource requested
Automation: change resistance signals in Ops floor — CM intervention
Upskilling: room availability conflict for Wave 2 — reschedule needed
Next 30-Day Focus
O2C: go-live pilot in region 1 — week 8 target
ERP: complete data cleansing; QA sign-off by week 6
Automation: UAT sign-off and user training pack
Compliance: mobilise legal; complete GDPR audit — priority red
Portal: finalise UX revisions; re-baseline vendor timeline

## Slide 11
STANDARD OPERATING PROCEDURE
Layout A
SOP — Process One-Pager
Step-by-step instructions, exception handling, and version control in one view
S | B · SOP Template · soufianeboudarraja.com
Process Name:
Invoice Processing — Accounts Payable
Owner:
Finance Ops Lead
Trigger:
Invoice received from vendor
Version:
v1.2
Review Date:
__/__/____
1
Receive Invoice
Log receipt in AP system — date-stamp and assign reference number
2
Validate PO Match
3-way match: PO number, goods receipt, and invoice amount
3
Approval Routing
Route to budget owner for sign-off if amount > €5,000
4
Coding & Entry
Assign cost centre, GL code, and payment terms in ERP
5
Payment Run
Batch process on agreed schedule (Tues/Thurs) — export to bank
6
Exception Handling
Flag mismatches — hold payment, notify vendor, document reason
7
Reconciliation
Monthly: reconcile AP ledger to bank statement — clear all holds
8
Archive & Audit Trail
Store original invoice + approval trail for 7 years (GDPR/tax)
Tools: ERP (SAP / D365) · AP portal · Bank payment module | Exception: If no PO exists → raise purchase req. before approval

## Slide 12
STANDARD OPERATING PROCEDURE
Layout B
SOP — Swimlane View
Who performs each step — cross-functional handoffs at a glance
S | B · SOP Template · soufianeboudarraja.com
Role
1
2
3
4
5
6
7
8
AP Clerk
✓
Receive Invoice
✓
Route for Approval
✓
Code & Post to ERP
✓
Archive & Audit
Budget Owner
✓
Budget Owner Approves
Finance Mgr
✓
Bank Reconciliation
IT / ERP System
✓
PO Match Check
✓
ERP Payment Run

## Slide 13
STANDARD OPERATING PROCEDURE
Layout C
SOP — Blank Template
Fill in your process: trigger, steps, exceptions, tools, and version
S | B · SOP Template · soufianeboudarraja.com
Process Name:
Owner:
Trigger / Input:
Version:
Review Date:
1
Step title
2
Step title
3
Step title
4
Step title
5
Step title
6
Step title
7
Step title
8
Step title
Tools / Systems used: | Exception handling: | Approval required from:

## Slide 14
S | B RESOURCES
Governance
& Risk
Light Version · All templates optimised for printing and sharing
Risk Assessment Template
Governance Structure One-Pager
Transformation Initiative Status Report
Standard Operating Procedure (SOP)
soufianeboudarraja.com | Light Version

## Slide 15
RISK ASSESSMENT TEMPLATE
Layout A
Risk Register
Log, score, and own every risk — update at each governance checkpoint
S | B · Risk Assessment · soufianeboudarraja.com
Low 1–3
Medium 4–7
Med-High 8–14
High 15–25
#
Risk Description
Category
Likelihood
(1–5)
Impact
(1–5)
Score
Owner
Mitigation Action
Review
Date
1
Financial
4
5
20
CFO
2
Operational
3
4
12
Ops Lead
3
Compliance
5
4
20
Legal
4
Reputational
2
3
6
Comms
5
Technology
3
4
12
CTO
6
Operational
4
3
12
Ops Lead
7
Financial
2
3
6
Finance
8
Technology
3
4
12
IT Mgr
9
Compliance
4
3
12
Legal
10
Reputational
2
2
4
HR

## Slide 16
RISK ASSESSMENT TEMPLATE
Layout B
Risk Heat Map
Plot each risk by likelihood and impact — prioritise the top-right quadrant
S | B · Risk Assessment · soufianeboudarraja.com
IMPACT →
LIKELIHOOD →
1
5
2
4
3
3
4
2
5
1
5
10
15
20
25
4
8
12
16
20
3
6
9
12
15
2
4
6
8
10
1
2
3
4
5
1
2
3
4
5
6
Risk Reference
1
Data Privacy Breach
2
Budget Overrun
3
Change Resistance
4
Regulatory Fail
5
Scope Creep
6
Vendor Delay
CRITICAL
LOW

## Slide 17
RISK ASSESSMENT TEMPLATE
Layout C
Risk Summary — Card View
One card per priority risk — use for leadership briefings and steering reviews
S | B · Risk Assessment · soufianeboudarraja.com
20
R1
Data Privacy Breach
Compliance
Owner:
Legal
Mitigation:
2FA, data retention policy, GDPR audit Q3
12
R2
Budget Overrun
Financial
Owner:
CFO
Mitigation:
Monthly budget gate review + variance alert
15
R3
Change Resistance
Operational
Owner:
HR / CM
Mitigation:
Training programme + Q&A channels + sponsor comms
8
R4
Regulatory Non-Compliance
Compliance
Owner:
Legal
Mitigation:
Compliance checklist at design gate
6
R5
Scope Creep
Operational
Owner:
PMO
Mitigation:
Change control board + weekly scope check
3
R6
Vendor / System Delay
Technology
Owner:
IT Lead
Mitigation:
SLA clauses + parallel workstream contingency

## Slide 18
GOVERNANCE STRUCTURE
Layout A
Governance Structure — Three-Tier Model
Who decides, who executes, and who adapts — at each level of the organisation
S | B · Governance Structure · soufianeboudarraja.com
TIER 1
Steering Committee
Sets strategy, approves major budgets and scope, resolves cross-functional escalations
Can decide:
Approve / reject initiatives over €50K · Change strategic direction · Resolve governance disputes
Members:
CxO sponsors · Finance lead · Ops · IT · Risk / Legal
Cadence: Monthly + ad hoc escalations
↓ escalates to
TIER 2
Project & Programme Teams
Plans, executes, and tracks delivery. Manages day-to-day decisions within approved scope
Can decide:
Approve implementation details · Manage timelines and dependencies · Escalate risks to Tier 1
Members:
PMO lead · Process owners · SMEs · Data analysts · Change managers
Cadence: Weekly stand-up + bi-weekly steering update
↓ escalates to
TIER 3
Local / Operational Teams
Implements changes in the field. Adapts within defined limits. Raises local risks and blockers
Can decide:
Adapt processes within approved scope · Raise issues to Tier 2 · Validate change effectiveness
Members:
Front-line managers · Ops staff · Local IT · Quality reps
Cadence: Daily ops + weekly sync with Tier 2

## Slide 19
GOVERNANCE STRUCTURE
Layout B
Decision Rights Matrix
Which decisions each tier owns, approves, or is consulted on
S | B · Governance Structure · soufianeboudarraja.com
D
Decide
A
Approve
C
Consult
I
Inform
Decision
Steering
Committee
Project
Team
Local /
Ops Team
Initiative launch / kill
D
C
I
Budget approval (> €50K)
D
C
I
Budget approval (< €50K)
C
D
I
Scope change (major)
D
C
I
Scope change (minor)
I
D
C
Risk escalation response
D
C
I
Process design choices
C
D
I
Tool / vendor selection
A
D
C
SOP sign-off
A
D
C
Staff communications
C
D
I
Local process adaptation
I
C
D

## Slide 20
GOVERNANCE STRUCTURE
Layout C
Governance Cadence Planner
Set your rhythm — who meets when, what they decide, and what they report up
S | B · Governance Structure · soufianeboudarraja.com
Forum / Meeting
Tier
Attendees
Agenda
Output
DAILY
Ops Stand-up
T3
Local ops team
Blockers / output review
Action items
WEEKLY
Project Stand-up
T2
PMO + workstream leads
Progress / risks / decisions
Status update + decisions
Risk Review
T2
PMO + Risk
Top 5 risk status
Mitigation actions
BI-WEEKLY
Steering Update
T1
Committee + PMO
Portfolio health / escalations
Decisions + guidance
MONTHLY
Steering Committee
T1
All CxO + PMO lead
Strategy, budget, priorities
Approved changes / decisions
Budget Review
T1
Finance + CxO
Spend vs. plan + variances
Budget adjustments
QUARTERLY
Governance Review
T1
Full committee
Health check / lessons / roadmap
Updated governance charter

## Slide 21
TRANSFORMATION STATUS REPORT
Layout A
Initiative Status Report
Quarterly view: status, milestones, risks, budget variance, and next actions
S | B · Status Report · soufianeboudarraja.com
Initiative
Owner
RAG
Key Milestone
This Period
Top Risk /
Mitigation
Budget
Variance
Decision
Needed
O2C Process Redesign
J. Müller
G
Value-stream map signed off
IT dep. delay / parallel workstream
+2%
Approve scope ext.
ERP Data Migration
S. Li
A
Data cleansing 60% complete
Quality gaps / daily QA sprint
+9%
Release contingency
Automation Wave 1
A. Patel
G
Invoice bot live in UAT
Low adoption / change mgmt boost
-3%
Compliance Uplift
M. Garcia
R
GDPR audit overdue
Regulatory breach / legal mobilised
+18%
Escalate to Tier 1
Workforce Upskilling
T. Nguyen
G
30 staff trained (Wave 1)
Availability / stagger schedule
0%
Customer Portal MVP
L. Brown
A
UX design delayed 2 weeks
Vendor lag / interim resource
+6%
Approve resource

## Slide 22
TRANSFORMATION STATUS REPORT
Layout B
Initiative Dashboard — Card View
One card per initiative — use for exec briefings and steering reviews
S | B · Status Report · soufianeboudarraja.com
ON
TRACK
O2C Process Redesign
Owner: J. Müller
72% complete
Risk: IT dependency
Next: Pilot go-live: wk 8
AT
RISK
ERP Data Migration
Owner: S. Li
48% complete
Risk: Data quality
Next: QA sprint complete: wk 6
ON
TRACK
Automation Wave 1
Owner: A. Patel
85% complete
Risk: Adoption
Next: UAT sign-off: wk 5
OFF
TRACK
Compliance Uplift
Owner: M. Garcia
22% complete
Risk: GDPR audit
Next: Legal review: urgent
ON
TRACK
Workforce Upskilling
Owner: T. Nguyen
60% complete
Risk: Availability
Next: Wave 2 kick-off: wk 9
AT
RISK
Customer Portal MVP
Owner: L. Brown
38% complete
Risk: Vendor lag
Next: UX revision: wk 7

## Slide 23
TRANSFORMATION STATUS REPORT
Layout C
30-Day Action Plan
Decisions needed from leadership, blockers, and the next 30-day sprint
S | B · Status Report · soufianeboudarraja.com
Decisions Needed
Release contingency budget for ERP migration (Owner: CFO — by Fri)
Approve resource for Customer Portal MVP (Owner: CxO — by EOW)
Escalate Compliance Uplift to Tier 1 — GDPR audit at risk
Confirm Wave 2 training schedule with HR (Owner: T. Nguyen — wk 9)
Sign off O2C pilot scope extension (Owner: Steering Comm. — wk 8)
Active Blockers
ERP: data quality issues slowing migration — QA sprint needed
Compliance: GDPR audit not started — legal escalation raised
Portal: vendor 2 weeks behind — interim resource requested
Automation: change resistance signals in Ops floor — CM intervention
Upskilling: room availability conflict for Wave 2 — reschedule needed
Next 30-Day Focus
O2C: go-live pilot in region 1 — week 8 target
ERP: complete data cleansing; QA sign-off by week 6
Automation: UAT sign-off and user training pack
Compliance: mobilise legal; complete GDPR audit — priority red
Portal: finalise UX revisions; re-baseline vendor timeline

## Slide 24
STANDARD OPERATING PROCEDURE
Layout A
SOP — Process One-Pager
Step-by-step instructions, exception handling, and version control in one view
S | B · SOP Template · soufianeboudarraja.com
Process Name:
Invoice Processing — Accounts Payable
Owner:
Finance Ops Lead
Trigger:
Invoice received from vendor
Version:
v1.2
Review Date:
__/__/____
1
Receive Invoice
Log receipt in AP system — date-stamp and assign reference number
2
Validate PO Match
3-way match: PO number, goods receipt, and invoice amount
3
Approval Routing
Route to budget owner for sign-off if amount > €5,000
4
Coding & Entry
Assign cost centre, GL code, and payment terms in ERP
5
Payment Run
Batch process on agreed schedule (Tues/Thurs) — export to bank
6
Exception Handling
Flag mismatches — hold payment, notify vendor, document reason
7
Reconciliation
Monthly: reconcile AP ledger to bank statement — clear all holds
8
Archive & Audit Trail
Store original invoice + approval trail for 7 years (GDPR/tax)
Tools: ERP (SAP / D365) · AP portal · Bank payment module | Exception: If no PO exists → raise purchase req. before approval

## Slide 25
STANDARD OPERATING PROCEDURE
Layout B
SOP — Swimlane View
Who performs each step — cross-functional handoffs at a glance
S | B · SOP Template · soufianeboudarraja.com
Role
1
2
3
4
5
6
7
8
AP Clerk
✓
Receive Invoice
✓
Route for Approval
✓
Code & Post to ERP
✓
Archive & Audit
Budget Owner
✓
Budget Owner Approves
Finance Mgr
✓
Bank Reconciliation
IT / ERP System
✓
PO Match Check
✓
ERP Payment Run

## Slide 26
STANDARD OPERATING PROCEDURE
Layout C
SOP — Blank Template
Fill in your process: trigger, steps, exceptions, tools, and version
S | B · SOP Template · soufianeboudarraja.com
Process Name:
Owner:
Trigger / Input:
Version:
Review Date:
1
Step title
2
Step title
3
Step title
4
Step title
5
Step title
6
Step title
7
Step title
8
Step title
Tools / Systems used: | Exception handling: | Approval required from: