## 90-Day Roadmap
PL-03 · 90-Day Quick-Wins Roadmap
Three-phase grid · Map & Diagnose → Pilot & Test → Embed & Govern · Delta column tracks before/after per initiative
INITIATIVE: |  |  | OWNER: |  | START DATE: |  | TARGET: |  | QUARTER:
MONTH 1 — MAP & DIAGNOSE |  |  | MONTH 2 — PILOT & TEST |  |  | MONTH 3 — EMBED & GOVERN |  |  | DELTA — BEFORE → AFTER
INITIATIVE / ACTION | OWNER | STATUS | INITIATIVE / ACTION | OWNER | STATUS | INITIATIVE / ACTION | OWNER | STATUS | METRIC + CHANGE
Map current-state process (value-stream) | Ops Lead | DONE | Run targeted pilot (1 process area) | PM / Ops | IN PROGRESS | Finalise SOP and governance playbook | COO / Lead | NOT STARTED | e.g. 30% cycle time reduction
Set KPI baselines (time, cost, error rate) | Analytics | DONE | Measure pilot results vs baseline | Analytics | IN PROGRESS | Roll out to all teams + embed training | HR / Ops | NOT STARTED | e.g. DSO -X days
Identify top 3 friction / handoff points | PM Team | DONE | Automate quick win #1 | IT / Ops | IN PROGRESS | Decommission legacy workaround | IT Lead | NOT STARTED | e.g. X hrs/yr saved
STATUS KEY: NOT STARTED ¦ IN PROGRESS ¦ DONE ¦ AT RISK | [8 empty] | Delta = measurable before/after result per initiative
Referenced in: SP-EP1, L1-EP3, L3-EP6 ¦ Business Transformation & Operational Governance Uncovered ¦ v1.0 ¦ March 2026 | [8 empty] | S ¦ B

## O2C Worked Example
PL-03 · Worked Example — O2C Transformation Sprint
Initiative: O2C Process Transformation ¦ Owner: COO / Finance Director ¦ Start: Q2 ¦ Target: 30% cycle time reduction + $276M cash unlock
MONTH 1 — MAP & DIAGNOSE |  |  | MONTH 2 — PILOT & TEST |  |  | MONTH 3 — EMBED & GOVERN |  |  | DELTA — RESULT
INITIATIVE / ACTION | OWNER | STATUS | INITIATIVE / ACTION | OWNER | STATUS | INITIATIVE / ACTION | OWNER | STATUS | METRIC + CHANGE
Map full O2C flow (value-stream) | Ops Lead | DONE | Automate invoice comparison | Finance | DONE | Standardise credit approval SOP | Finance | DONE | 9,000 hrs/yr saved
Baseline KPIs: DSO, backlog age | Analytics | DONE | Pilot backlog prioritisation model | Sales Ops | DONE | Embed backlog review cadence | COO | IN PROGRESS | DSO -8 days
Identify top 3 handoff friction pts | PM Team | DONE | Redesign handoff protocol | Ops Lead | DONE | Train all teams on new protocol | HR / Ops | IN PROGRESS | Handoff errors -40%
Map credit decision bottleneck | Finance | DONE | Implement auto-approval rules | IT / Finance | IN PROGRESS | Governance review: credit limits | CFO | NOT STARTED | Credit cycle -3 days
Diagnose billing accuracy gaps | Billing | DONE | Pilot invoice validation checklist | Billing | AT RISK | Automate validation logic | IT | NOT STARTED | Billing errors -22%
90-day result: $276M trapped cash unlocked ¦ 84,000+ staff hours saved ¦ DSO reduced by 8 days ¦ Handoff errors down 40%
Referenced in: SP-EP1, L1-EP3, L3-EP6 ¦ Business Transformation & Operational Governance Uncovered ¦ v1.0 ¦ March 2026 | [8 empty] | S ¦ B