## Sheet1
COMMUNITY ASSOCIATION
SAMPLE ANNUAL CALENDAR - 2020
| Resp | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
This is a smaple calendar, containing a few examples of task items, assignments, and options for data that may be included in grid boxes to help you create the management plan for ytour community. For more details, please see the blog "The Annual Calendar - A Key Component to Management Success" at www.tomasuarusrexblog.com. For assistance in creating your calendar, please contact us at tom@associationbridge.com.
I. ADMINISTRATIVE - GENERAL
Annual Calendar - Prepare next year calendar (see Budget) | Mgmt | bar: DEC
Annual Meeting - Verify Schedule, Timeline | BOD | bar: JUN
Annual Meeting - Book Date with Independent Election/Proxy Service (or decide no service needed) | Mgmt | bar: JUN
Annual Meeting - Pre-Meeting SOP | Mgmt | bar: JUL
Annual Meeting - Call for Nominations | Mgmt | JUL: 30th
Annual Meeting - Nominations Due | Mgmt | AUG: 30th
Annual Meeting - Verify Officer & Committee Reports | Mgmt | SEP: 1st
Annual Meeting - Send Notice (incl. annual MCCCOC notice) | Mgmt | SEP: 15th
Annual Meeting - Meet the Candidates Night |  | SEP: 20th
Annual Meeting - Hold |  | OCT: 15th
Annual Meeting - Post Meeting SOP | Mgmt | bar: OCT
Audit - Confirm Schedule for Fieldwork | Mgmt
Audit - Receive First Draft | Mgmt
Audit - Review | BOD
Audit - Approve | BOD
Budget - Solicit comments (BOD,Staff) | Mgmt
Budget - Prepare first draft | Mgmt
Budget - Draft to BOD | Mgmt
Budget - Approval of Draft | BOD
Budget - Proposed Budget Mailed to Owners | Mgmt
Budget - Special Meeting to Review With Owners (if Needed) | BOD
Budget - Approval | BOD
Budget - Copy to accounting dept, verify fees | Mgmt
Budget - Prepare next year budget spread | Mgmt
Committees - Review/Confirmation of Chairs & Members | BOD
Community Info Sheet - Review & Update | Mgmt | bar: JAN; APR; JUL; OCT
File Purge/Archive | Mgmt | bar: DEC
Resale Documents - Review & Update | FSR
Resident Information Package - Review & Update as Needed | Mgmt
Routine Resident Communication - Contact Info Updates | Mgmt
Routine Resident Communication - BuildingLink Tips | Mgmt
Routine Resident Communication - Energy Conservation Tips | Mgmt
Routine Resident Communication - Insurance C of I Request Process | Mgmt
Routine Resident Communication | Mgmt
Routine Resident Communication | Mgmt
Routine Resident Communication | Mgmt
Routine Resident Communication | Mgmt
Tax Returns - Receive from Auditor | Mgmt
Tax Returns - Review and Sign | BOD
Tax Returns - Facilitate Filing (Fed due 5/15, State due 6/15) | Contr
II. ADMINISTRATIVE- CONTRACT
Audit - RFP | Mgmt | MAR: 2021
Audit - Receive Proposals | Mgmt | APR: 2021
Audit - Award Contract | BOD | MAY: 2021
Elevator - RFP | Mgmt | bar: FEB
Elevator - Receive Proposals | Mgmt | bar: MAR
Elevator - Award Contract | BOD | bar: APR
Elevator - End Contract Term |  | MAY: 31st
Fitness Equipment - RFP | Mgmt | bar: NOV
Fitness Equipment - Receive Proposals | Mgmt | bar: DEC
Fitness Equipment - Award Contract | BOD | bar: JAN
Fitness Equipment - End Contract Term/Anniversary | bar: FEB
Insurance (Master) - RFP | Contr | bar: MAR
Insurance (Master) - Receive Proposals | Mgmt | bar: APR
Insurance (Master) - Review with Broker, Award Contract | BOD | bar: MAY
Insurance (Master) - End Contract Term/Anniversary |  | JUN: 9th
III. BOARD OF DIRECTORS & COMMITTEES
Board Meeting - Regular | BOD
Board Annual Planning Meeting | BOD
Annual Policy Review | BOD
_____________Committee Meeting | Cmte
_____________Committee Meeting | Cmte
_____________Committee Meeting | Cmte
IV. PREVENTIVE / SCHEDULED MAINTENANCE
(Note: Daily/weekly items not included)
Asphalt Inspections | Mgmt
Backflow Preventers - Annual Test | Contr
Boiler Inspection (bi-annual) | Contr
Carpet Cleaning - Water Extraction (3 Years) | Contr | APR: 2022
Carpet Cleaning - Low Moisture Cleaning | Contr | bar: APR
Concrete Inspections | Mgmt
Concrete Repairs | Contr | bar: MAY
Electrical Panel/Switchgear Infrared Test | Contr | bar: APR
Electrical Panel/Switchgear Maintenance - Schedule PEPCO | Mgmt | MAR: 2021
Electrical Panel/Switchgear Maintenance | Contr | APR: 2021
Elevators - Annual Safety Test | Contr | bar: JUN
Elevators - 5 Year Full Load Test | Contr | JUN: 2023
Emergency Generator - test and run | Staff | bar: JAN to DEC
Emergency Generator - Manual Load Test | Staff | bar: JAN to DEC
Emergency Generator - Full Load Test | Contr | bar: DEC
Emergency Generator - Tune up/Inspect | Contr | bar: JUN
Fire curb painting | Staff | bar: MAR; JUL; SEP; NOV
Hose Bibb - Activation/shut down | Staff
Landscaping - Spring Clean-up | Contr | bar: APR
Landscaping - Fertilization of Trees and Shrubs | Contr
Landscaping - Turf Pre-Emergent Weed Control & Fertilization | Contr
Landscaping - Turf Grub & Insect Control | Contr | bar: JUN
Landscaping - Slow Release Fertilizer | Contr | bar: SEP; NOV
Landscaping - Turf Overseeding/Aeration | Contr | bar: SEP
Landscaping - Leaf Removal | Contr | bar: DEC
Lighting inspection - exterior | Staff | bar: JAN to DEC
V. PROJECTS
Capital Projects
Fire Protection Equipment - Draft Specification, RFP & Bidders List | Eng | bar: JAN to FEB
Fire Protection Equipment - Confirm Bidders List, Approve RFP Package | BOD | bar: FEB
Fire Protection Equipment - RFP | Eng | bar: FEB
Fire Protection Equipment - Bids Received, Analysis & Recommendation to Board | Eng | bar: MAR
Fire Protection Equipment - Approval | BOD | bar: FEB; APR
Fire Protection Equipment - Perform Project | Contr | bar: JUL to NOV
Garage Door Replacement - RFP | Mgmt | bar: MAR
Garage Door Replacement - Receive Bids | Mgmt | bar: APR
Garage Door Replacement - Award Contract | BOD | bar: MAY
Garage Door Replacement - Perform Project | Contr | bar: JUN
Management/Administrative Projects
Front Desk Resource Guide - Edit | Mgmt | bar: DEC
Front Desk Resource Guide - Complete | Mgmt
Front Desk Resource Guide - Staff Meeting to Review | Mgmt
Welcome Package - Draft | Mgmt
Welcome Package - Edit | Mgmt
Welcome Package - Complete | Mgmt
Policy Projects
Rule Revisions - Committee Meetings | Cmte | bar: JAN to APR
Rule Revisions - Recommendations Submitted to Board | Cmte | bar: APR
Rule Revisions - Board Review | BOD | bar: MAY
Rule Revisions - Legal Review | Atty | bar: MAY to JUN
Rule Revisions - Board Approval of Draft | BOD | bar: JUN
Rule Revisions - Proposed Rules Sent to Membership for Comment | Mgmt | bar: JUN
Rule Revisions - Town Hall Meeting | BOD | bar: JUL
Rule Revisions - Approval | BOD | bar: AUG
Rule Revisions - Communication to Owners | Mgmt | bar: AUG
Rule Revisions - Update Welcome Package, BuildingLink, Resale Disclosure Package. | Mgmt | bar: AUG
Financial Projects
Reserve Study - RFP | Mgmt
Reserve Study - Bids Received | Mgmt
Reserve Study - Contract Approved | BOD
Reserve Study - Perform Study | Contr
Maintenance Projects
Interior Signage - Obtain Design Options | Mgmt | bar: FEB
Interior Signage - Select Design | BOD | bar: MAR
Interior Signage - RFP | Mgmt | bar: APR
Interior Signage - Receive Proposals | Mgmt | bar: MAY
Interior Signage - Award Contract | BOD | bar: JUN
Interior Signage - Install Signs | Staff | bar: JUL
VI. DEFERRED PROJECTS for 2021 reconsideration
Ad Hoc Marketing Committee
Asphalt
Balconies
Bylaw Amendment - No Smoking (other?)
Car Wash Station